# Affiliate Program — Bootstrap

Inherits from: ~/.claude/templates/session-kickoff-bootstrap.md

Use when: launching, overhauling, or operating an affiliate marketing program — network-based (CJ, Impact, Rakuten, Awin, ShareASale), in-house, or creator-commerce (ShopMy, LTK).

## Who this is for

Affiliate marketers, partnerships leaders, performance-marketing leads at DTC / ecommerce / subscription brands. Programs span 12-24 weeks for structured launch or ongoing optimization.

## Opinionated defaults

### Network vs. in-house vs. hybrid

- Network (CJ / Impact / Rakuten / Awin / ShareASale / Pepperjam): faster to launch, built-in affiliate base, more overhead cost

- In-house: higher margin, more control, requires tech infrastructure (Refersion, Tapfiliate, LeadDyno, custom)

- Hybrid: creator / content affiliates in-house; mass / coupon on network

- Default recommendation: start on network, move to in-house at $1M+ annual affiliate revenue

### Affiliate types (distinct strategies)

- Content affiliates (NYT Wirecutter, Business Insider Reviews, review sites): highest value; long-form content; 3-12 month recruitment cycles

- Creator affiliates (Instagram / TikTok / YouTube creators): content + audience; overlap with influencer program

- Coupon affiliates (RetailMeNot, Honey, Capital One Shopping): last-click grabbers; low-intent; limit commission

- Cashback sites (Rakuten, Ebates): last-click; fraud risk; consider exclusion or capped commission

- Loyalty apps (Ibotta, Fetch): last-click coupon-adjacent

- Email affiliates / media buyers (newsletter monetization, display partners)

- Employee / customer referral (often bundled with loyalty, separate from affiliate)

### Commission structure

- Ecom: 5-15% typical for non-coupon affiliates; 1-5% for coupon

- SaaS: 20-30% first-year revenue; often recurring for 12-24 months

- Tiered commission: higher rates for top-performing affiliates

- Exclusive codes: for top affiliates (offer unique % discount with dedicated tracking)

- Performance bonuses: monthly bonuses for exceeding thresholds

### Cookie / attribution window

- 7-30 days typical for ecom

- 60-90 days for SaaS

- Last-click within window: standard industry

- Cross-device tracking increasingly important (Impact, Everflow, AvantLink specialize)

### Attribution conflicts

- Coupon affiliates vs. paid / creator: coupon affiliate gets last-click credit on someone who was originally driven by creator or paid ad — controversial

- De-duplication logic: preferred-channel priority rules; cookie-last-seen vs. cookie-first-seen

- Non-commissioning on branded search: affiliates bidding on brand terms is cannibalistic; ban in terms

### Fraud prevention

- IP + device fingerprinting — multiple orders from same IP/device across different affiliates

- Order-pattern analysis — unusual velocity, geographic clustering, payment-method concentration

- Cookie-stuffing detection — invalid cookies, suspicious referrer strings

- Void fraudulent orders — chargeback affiliate; terminate if pattern continues

### Program launch

- Start with content + creator affiliates — cleaner attribution, brand-safe

- Add coupon network later (or never) — they last-click-grab but can add margin-free revenue

- Recruit top-20 affiliates at launch — personally onboard; they set the tone

- Commission ladder published — transparency + motivation

### Creator commerce (ShopMy, LTK, etc.)

- Adjacent to influencer program — often merged in DTC

- Creator-owned audience + shoppable content

- Commission 10-20% typical; sometimes higher for exclusives

- Different attribution model — creator-code-based rather than cookie-based

## Step 0 — Interview question additions

- Current affiliate state — program exists? Network? In-house?

- Revenue attribution today — affiliate share of revenue

- Cookie / attribution window in use

- De-duplication logic — what happens when affiliate + paid ad both touch?

- Fraud detection capability — manual review? Tool?

- Commission structure — flat or tiered?

- MAP policy — enforceable on affiliate sites?

- Top existing affiliates — who are they, what channels, what performance?

- Content affiliate relationships — Wirecutter / NYT / review sites?

- Creator commerce overlap — ShopMy / LTK program exists?

- Network contracts (if applicable) — terms, exclusivity, override rates?

## Step 2 — Milestone template (16-week program)

### M1 — Program Design + Infrastructure (week 1-4)
- Deliverable: affiliate strategy, network decision, commission structure, fraud logic, T&C
- Validation: legal-reviewed T&C; attribution logic tested
- Target: end of week 4

### M2 — Launch Infrastructure (week 4-6)
- Deliverable: network contracts signed OR in-house tool deployed; tracking integrated
- Validation: test orders tracked correctly end-to-end; commissions calculated correctly
- Target: end of week 6

### M3 — Affiliate Recruitment Wave 1 (week 6-10)
- Deliverable: top-50 affiliate outreach; content + creator focus; contracts signed
- Validation: 20+ active affiliates driving traffic
- Target: end of week 10

### M4 — Coupon + Scale Affiliates (week 10-12)
- Deliverable: coupon network activation (if included); scaled affiliate base
- Validation: program producing meaningful revenue; fraud detection operational
- Target: end of week 12

### M5 — Optimization + Reporting (week 12-15)
- Deliverable: performance dashboard; affiliate-by-affiliate management cadence; tier movements
- Validation: top-affiliate-driven revenue concentrated but diverse
- Target: end of week 15

### M6 — Ongoing Program (week 15+)
- Deliverable: monthly review cadence; quarterly commission + program review; ongoing recruitment
- Validation: program self-operates; performance sustained
- Target: end of week 16+

## Step 3 — Critical mental model

Affiliate is partnership, not channel.

Treating affiliate as "another ad channel" produces coupon-dominated programs with poor margins. Treating affiliate as partnership produces content-driven programs with high margins, brand alignment, and compound value.

The 80/20 of well-run programs: 20% of affiliates produce 80% of revenue. Those top affiliates are managed like business partners — personal relationships, exclusive offers, co-created content, early access. The bottom 80% are self-service.

Programs that treat all affiliates the same (flat commission, no relationship management, no content support) optimize for coupon-site last-click grabbers and leave the content / creator upside on the table.

## Step 4 — Domain validators

- Tracking integrity: test orders trace end-to-end

- Fraud detection operational: detection rules firing on suspicious patterns

- Commission calculation accurate: no systematic errors

- Affiliate segmentation: content / creator / coupon / cashback tracked separately

- De-duplication working: cross-channel attribution conflicts resolved per policy

## Step 8 — Working protocol additions

- Never let affiliates bid on brand terms — cannibalistic

- Never pay for fraud — void + chargeback + terminate

- Never treat all affiliates same — segment, manage top-20 personally

- Never skip MAP enforcement on affiliate sites

- Always publish commission ladder — transparency motivates

- Always document de-duplication rules — affiliates will challenge; be clear

- Always review top-20 affiliates monthly — relationships compound

## KB integration

- {{KNOWLEDGE_BASE_ROOT}}/mmm-and-response-curves/wiki/_index.md — attribution methodology (affiliate fits multi-touch model)

- {{KNOWLEDGE_BASE_ROOT}}/retail-sales-enablement/wiki/_index.md — partnership-management frameworks

## Common example fills

- "Launch affiliate program on Impact for $25M DTC brand — network-based; target 10% of revenue within 12 months"

- "Migrate from CJ to in-house (Refersion) for $50M brand — 16-week migration without revenue disruption"

- "Add content affiliate strategy — recruit Wirecutter, Business Insider Reviews, top review sites"

- "Creator-commerce program launch via ShopMy for fashion DTC — 100 creator partnerships in 90 days"

- "Fraud investigation + remediation — coupon affiliate showing anomalous velocity; audit + terminate if fraud"

## Hand-off

After bootstrap, use ~/.claude/templates/growth-ecommerce/affiliate/resumption.md.