# Brand Positioning / Rebrand Program — Resumption

Inherits from: ~/.claude/templates/session-kickoff-prompt.md

## Session scope examples

- "Customer interview synthesis"

- "Positioning workshop with leadership"

- "Visual direction review + selection"

- "Retail partner sync — Target + Whole Foods packaging reset"

- "Post-launch brand-tracker review"

- "Voice-chart iteration based on draft feedback"

## Blocker questions

- Is internal alignment locked on positioning? If leadership disagrees, design work is premature — re-align first.

- Any trademark / legal issue on new name / mark? Resolve before visual build.

- Any retail partner timeline hard-stop? Retail resets happen twice a year; miss the window and wait 6 months.

- Any customer research contradicting the direction? Don't bury contradiction; decide whether to update direction or explain why research is discounted.

- Any active PR / brand event that should coordinate with launch timing?

## Ranked work patterns

### If positioning is pre-alignment

Do not move to visual / voice work. Alignment first. Options:

- Workshop with leadership to surface disagreements

- Customer research to ground the argument in data

- Stakeholder interviews to understand what they're really defending

- Positioning options test (3 versions, show customers) to let data decide

### If positioning is locked, visual is pending

Standard sequence: moodboards → primary direction → logo → color → type → photography → application → asset library.

### If visual is done, rollout is pending

Coordinate:

- Internal team training

- Retail / wholesale partner lead time (packaging, POP)

- DTC site update + email templates

- Amazon / marketplace listings

- Social channels

- PR + launch moment

### If post-launch measurement is needed

Brand tracker: unaided awareness, aided awareness, consideration, preference, NPS — monthly baseline for 12+ months post-launch to measure equity trend.

## Working protocol additions

- Never ship visual work while positioning is in debate

- Never skip retail partner lead times

- Never launch rebrand without post-launch brand tracker — you need measurement

- Never skip legal review on new names / marks / claims

- Always document every choice — 3 years later, someone will ask why

## Verification commands

# Positioning lock status
{stakeholder-alignment artifact}      # expect: explicit sign-off

# Asset library completeness
{template inventory}                   # expect: all planned assets delivered

# Legal clearance
{trademark + domain + handle status}   # expect: clear

# Retail sync
{retail partner lead time vs. timeline} # expect: lead times met

# Brand tracker baseline
{pre-launch measurement data}          # expect: baseline captured

## Common drift patterns

- Stakeholder-driven visual creep — every exec adds a requirement; ends up bland

- Late-stage positioning reopening — reset the project; resist

- Research over-indexing — customer research is input, not decision; brand leadership must still decide

- Retail sync underestimation — retail partners don't flex; plan accordingly

- Post-launch measurement deferral — without tracker, you can't know if it worked