# Launch / GTM Program — Bootstrap

Inherits from: ~/.claude/templates/session-kickoff-bootstrap.md

Use when: starting a new product / brand / service launch across DTC, retail, Amazon, subscription, B2B SaaS, or marketplace contexts.

## Who this is for

Growth leaders, brand managers, product marketing, ecommerce leads, founders running a go-to-market program for a new product, new category extension, new market entry, or relaunch. Standard program is 90 days (30+30+30 pre-launch / launch / scale); complex launches extend to 120-180 days.

## Opinionated defaults

### Launch windows

- 90-day launch: 30-day pre-launch + 30-day launch + 30-day scale

- 3 waves: seed list → broader audience → paid acceleration

- PR embargo: 72 hours pre-launch for coordinated media

- Hero assets created 30 days pre-launch — video, photography, copy, landing page, A+ Content (Amazon)

### Decision gates

- Day 0 gate: hero content / inventory / channel configs ready. Miss this and launch slips, not pushes forward.

- Day 30 gate: Is initial demand validated? CAC on target? Retention signal positive? Decision: scale / iterate / kill.

- Day 90 gate: Systematic economics. LTV trajectory. Channel mix proven. Decision: scale aggressively / optimize / wind down.

### KPIs by stage

- Pre-launch: list growth, pre-order count (if applicable), waitlist size

- Launch (Day 0-30): Day-0 revenue, first-week sell-through, inventory burn rate, CAC, review velocity, PR mentions

- Scale (Day 30-90): CAC stability, blended MER, repeat-purchase rate emerging, channel expansion signals

- Post-90: LTV:CAC trajectory, organic rank, brand-search trend

### Launch risks to plan for

- Inventory underestimation — if product takes off, run-out kills momentum; over-order if signal is strong

- PR timing collision — don't launch the week of a competitor launch or major industry event

- Platform policy snags — pre-approve Amazon listings, Meta ads, Google Shopping compliance 14+ days before launch

- Review burst management — seed reviewers in advance; Vine enrollment on Amazon; trusted creators ship pre-launch

- Channel readiness — email list, SMS list, DTC site, Amazon listing, retail placement all must be live coordinated

### What not to do

- Don't launch quietly hoping for organic — without coordinated paid + PR + owned channels, launches underperform by 60-80%

- Don't discount aggressively at launch — anchors price expectations low; hard to unwind

- Don't skip PR embargo structure — uncoordinated media creates confusion

- Don't launch in Q4 peak without 60-day lead time — inventory, ad auction CPMs, freight delays all compound

## Step 0 — Interview question additions

- Product / brand category — new SKU, new brand, category extension, geographic expansion?

- Channels in scope — DTC, Amazon, retail, wholesale, marketplace, B2B?

- Existing audience / list — how many existing customers / subscribers to lean on for seed wave?

- Target Day-30 revenue / AOV / units

- Inventory commitment — how many units? what's the risk if we over- or under-commit?

- Pricing + margin structure — gross margin at launch, scale margin, promotion depth available

- Competitive launch timing — any competitor launches or major events in the 90-day window?

- PR + influencer capacity — existing relationships, agency engagement, budget

- Paid media readiness — accounts structured, creative ready, compliance approved

- Retail / wholesale lead time — if retail, when do POs need to land?

- Brand positioning clarity — is the messaging locked, or still being tested?

- Risk appetite — is this a bet-the-company launch or one of many SKU launches?

## Step 2 — Milestone template (90-day / 13-week program)

### M1 — Pre-Launch Plan + Asset Production (week 1-4)
- Deliverable: launch plan (all channels), hero assets, landing page, email sequence, influencer packages
- Validation: hero video live, Day-0 channel content approved, ad campaigns configured but paused
- Target: end of week 4 (Day -7)

### M2 — Seed Wave + PR Embargo (week 4-5)
- Deliverable: seed list activated; PR embargo live; Day-0 countdown running
- Validation: pre-launch traffic at target; embargo press committed
- Target: end of week 5 (Day -1)

### M3 — Public Launch (week 5)
- Deliverable: Day-0 launch across all channels; PR mentions live; paid media launched
- Validation: Day-0 revenue hit target ±20%; no platform policy issues; inventory tracking
- Target: end of week 5 (Day 0)

### M4 — Scale Wave (week 6-9)
- Deliverable: paid media scaling by channel; creative iteration; retention flow activation
- Validation: Day-30 CAC <target; review velocity positive; no inventory crisis
- Target: end of week 9 (Day 30)

### M5 — Day-30 Gate Review + Iteration (week 9-10)
- Deliverable: Day-30 review; kill/iterate/scale decision; revised plan for next 60 days
- Validation: data-driven decision made; next-phase plan approved
- Target: end of week 10 (Day 37)

### M6 — Day-90 Retrospective + Scale Decision (week 13)
- Deliverable: Day-90 retrospective; LTV trajectory; channel mix; Year 1 plan
- Validation: full program learnings documented; next-phase funding / planning locked
- Target: end of week 13 (Day 90)

## Step 3 — Critical mental model

Launch day is not the end. It's the beginning of the real learning period.

The first 90 days reveal two things that pre-launch research cannot:

- Is there real demand? Pre-orders and waitlists are interest; paid acquisition at target CAC is demand.

- Is the GTM motion efficient? Channel mix, creative, pricing, audience — the combinatoric question only plays out with real spend.

Treat launch as a test, not a coronation. The first 30 days are hypothesis validation; the next 60 days are systematic optimization. Expect the plan to change — locking in on day 0 assumptions is the failure mode.

Most launches either: scale too fast on weak early signal (hubris) or too slow on strong early signal (caution). The Day-30 gate is designed to force an honest read.

## Step 4 — Domain validators

- Hero asset readiness — video, photography, copy, landing page, product listings (all channels) — 7 days pre-launch

- Inventory position — 60+ days of supply at target run-rate on launch day

- PR embargo integrity — embargo agreements signed, pre-launch previews seeded

- Channel readiness — ads approved, email sequence tested, SMS compliance clear, site load-tested

- Review seeding — Vine enrollment live (Amazon), seed reviewers shipped, micro-influencers under NDA

- Day-0 logistics — customer support staffed, fulfillment confirmed, shipping carriers notified

## Step 8 — Working protocol additions

- Never launch without 60+ days of inventory at target run-rate.

- Never launch without a Day-30 gate pre-agreed on what "success" means.

- Never discount aggressively at launch — anchors pricing low.

- Never scale paid before Day-14 — insufficient signal.

- Never ignore customer support tickets Day-0 through Day-7 — they are the leading indicator.

- Always write Day-30 and Day-90 retrospectives with data, not vibes.

- Always communicate launch plan to CX / Support / Ops / Finance — launches are cross-functional.

## KB integration

- {{KNOWLEDGE_BASE_ROOT}}/amazon-product-launches/wiki/_index.md — 9 articles; primary reference for Amazon launch playbooks

- {{KNOWLEDGE_BASE_ROOT}}/product-research-and-competitive-intelligence/wiki/_index.md — 12 articles; relevant for launch positioning + competitive landscape

- {{KNOWLEDGE_BASE_ROOT}}/retail-sales-enablement/wiki/_index.md — if retail is in the launch mix (33 articles on ShelfWins, planograms, buyer decks)

## Common example fills

- "Launch flagship pickleball paddle line (150−300 tier) across DTC + Amazon in 90 days; target $500K Day-30 revenue"

- "Launch new subscription tier for existing CPG brand; target 2,500 subscribers in 90 days at <$40 CAC"

- "Relaunch under-performing SKU on Amazon with new branding + A+ Content + PPC rebuild"

- "B2B SaaS product launch with PLG motion; target 500 signups in 30 days, 50 activations in 60 days"

- "International launch of existing DTC brand — UK/EU expansion; 90-day readiness + 90-day launch"

- "Retail launch into Target + Whole Foods parallel to DTC launch — coordinated 120-day plan"

## Hand-off

After bootstrap, use ~/.claude/templates/growth-ecommerce/launch-gtm/resumption.md.