# Launch / GTM Program — Resumption

Inherits from: ~/.claude/templates/session-kickoff-prompt.md

## Session scope examples

- "Day-0 readiness checklist pass"

- "Creative iteration for scale wave"

- "Day-30 gate review + decision"

- "Inventory replanning — sell-through faster than forecast"

- "PR opportunity response (major media inquiry Day 3)"

- "Launch-week crisis: platform policy strike on listing"

## Blocker questions

- Where are we in the 90-day window? (Pre-launch, launch, scale, post-30, post-90.) Different phases have different decision velocities.

- Any Day-0 or Day-30 gate decision pending? If yes, is the data clean?

- Any platform policy / compliance issue active? Amazon listing flag, Meta ad rejection, Google Merchant Center issue — fix before anything else during launch

- Any inventory / supply-chain crisis? Sell-through faster than forecast = scale throttle; slower = pacing check

- Any competitor action or market event that could shift the launch trajectory?

- Customer support signal? Day-0 to Day-7 CS volume / sentiment is the leading indicator of product fit

## Ranked work patterns

### Pre-launch phase (Day -30 to Day -1)

Priority: checklist completion. Every day's work ladders to Day-0 readiness. No distractions.

### Launch week (Day 0 to Day +7)

Priority: real-time monitoring. Watch:

- Inventory burn rate vs. forecast

- Platform health (ads approved, listings live, site performance)

- Customer support ticket velocity + themes

- PR mentions + sentiment

- Review velocity + rating

Decision authority: compressed; launches make decisions hourly, not weekly.

### Scale phase (Day 7 to Day 30)

Priority: creative iteration + channel mix optimization. What's working + why? What's dying + why? Start building the Day-30 gate data pack.

### Day-30 gate

Honest assessment:

- CAC vs. target

- Conversion rate vs. target

- Inventory sell-through

- Review velocity + rating

- Repeat-purchase signal (if enough time)

Decision: scale / iterate / kill. Do not push the decision — the data is sufficient at Day 30.

### Post-30 scale

Priority: systematic expansion. Channel-by-channel optimization. LTV signal watching. Retention flow activation.

### Day-90 retro

Full retrospective. What worked, what didn't, what was learned. Year-1 plan locked.

## Working protocol additions

- During launch week: make decisions fast; over-communicate with all stakeholders; assume something will go wrong

- Never break a pricing anchor in first 90 days unless it's the only path to viability

- Never scale paid before Day 14 unless signal is exceptional

- Never hide a Day-30 kill decision — even if it's hard, the data is the data

- Always document learnings — these compound across future launches

## Verification commands

# Day-0 readiness (pre-launch)
{checklist status}                  # expect: all items green 7 days before launch

# Launch health (launch week)
{inventory burn + ad approval status + CS tickets} # expect: monitored hourly

# Day-30 gate metrics
{CAC, CVR, inventory, reviews}      # expect: all tracked, benchmarked to plan

# Day-90 metrics
{LTV trajectory, channel mix, retention signal} # expect: evaluable by Day 90

## Common drift patterns

- Launch-day hubris — early positive signal gets extrapolated; paid scales too fast; creative doesn't iterate

- Launch-day fear — strong signal gets under-invested; inventory sits; opportunity missed

- Day-30 can't-let-go syndrome — weak signal gets "one more month" decisions; kill discipline matters

- Launch scope creep — "while we're launching, let's also launch Y" — kills focus

- Post-launch retrospective deferral — "we'll retro after Q" becomes "we never retro" — lock the date pre-launch