# UGC / Reviews Program — Bootstrap

Inherits from: ~/.claude/templates/session-kickoff-bootstrap.md

Use when: launching or overhauling a user-generated content or reviews program — solicitation flows, review-management, UGC rights capture, review-platform integration, response protocols.

## Who this is for

Ecommerce / DTC / consumer-brand teams managing reviews + UGC as a core acquisition + conversion lever. Programs span 8-16 weeks to launch or rebuild; ongoing after.

## Opinionated defaults

### Review fundamentals

- Review velocity matters more than count. 20 reviews this month > 200 reviews last year.

- Never pay for reviews. Never solicit positive-only. Both are policy violations (Amazon, FTC) and brand-integrity violations.

- Review content: photos + videos outperform text-only 2-3× in social proof value.

- Star-rating target: 4.3+ sustained. Below 4.0 signals product or experience issue; above 4.8 signals selection bias or fake.

### Review solicitation

- Post-purchase email: T+7 (delivered) + T+14 (usage) + T+30 (final)

- Incentivize participation, not positive outcome — discount on next purchase for any review is OK; discount for 5-star review is not

- Photo / video request: explicit — "share a photo" yields 5-10× photo content vs. passive

- SMS review requests: emerging pattern, strong performance (20-40% response rate)

- Review platform integrated with post-purchase flow (Yotpo / Okendo / Stamped / Loox / Judge.me / Junip)

### Review-response protocol

- Respond to all 1-3 star reviews within 48h publicly — shows brand cares

- Don't respond to 4-5 star reviews routinely — looks performative

- Private-channel follow-up for resolution — move issue off public review

- Never argue with reviewer publicly — always acknowledge + resolve

- Review disputes: only dispute obvious fraud / policy violations; never dispute honest negative

### UGC solicitation + rights

- Always capture usage rights — submission includes permission for brand use

- 90-day paid-ad usage + 1-year organic usage — standard terms

- Compensation for UGC: optional for regular customers; contracted for dedicated creators (see influencer-creator templates)

- UGC platforms: Yotpo Visual UGC / Bazaarvoice / Olapic / Pixlee TurnTo / Okendo — aggregate + curate

### Review platform choice

- Yotpo: enterprise-full-stack (reviews + loyalty + SMS + UGC); higher cost

- Okendo: modern UX, Shopify-native, strong for growing brands

- Stamped: mid-market, reviews + loyalty combo

- Loox: photo-first reviews, Shopify-ecosystem

- Judge.me: budget-friendly, solid core features

- Junip: newer, good UX, growing

- Reviews.io / Trustpilot: independent third-party; valuable for off-site trust signals

- Google Seller Ratings: requires third-party review platform integration

### Cross-posting + aggregation

- Post reviews to Google Seller Ratings — ad star-rating display

- Post to Trustpilot / BBB for brand trust

- Post to Yahoo / Bing Ads for multi-platform ad star-ratings

- Cross-post to Amazon — never — Amazon has strict TOS; paid promotion to post bans accounts

### Anti-patterns

- Never pay for reviews

- Never filter out negative reviews pre-publication (some platforms tempt this; strict FTC violation)

- Never "solicit only satisfied customers" — selection bias is fraudulent

- Never manufacture UGC (AI-generated, stock imagery presented as customer) — regulatory + trust risk

### Measurement

- Review velocity: reviews/month trend

- Review-to-purchase ratio: % of orders that produce review

- Average star rating: monthly

- UGC rate: % of submissions with photo/video

- Response coverage: % of 1-3 star with response within 48h

- Review-driven conversion impact: A/B test with vs. without on PDP

## Step 0 — Interview question additions

- Review platform in use — none, DIY, integrated?

- Current review count + rating — by SKU / overall

- Review solicitation flow — manual, automated, frequency?

- UGC capture — rights-cleared library exists?

- Response protocol — who responds, SLA, escalation?

- Photo/video capture rate — % of reviews with visual

- Cross-platform footprint — Google Seller Ratings, Trustpilot, BBB?

- Amazon review independence — separate or cross-functional team?

- SMS review capability — testing, deployed, not?

- Legal / compliance stance — any past review-fraud concerns or legal notices?

## Step 2 — Milestone template (12-week program)

### M1 — Audit + Platform Decision (week 1-3)
- Deliverable: current-state review audit; platform selection; response protocol definition
- Validation: clear gaps + strategy; platform committed
- Target: end of week 3

### M2 — Platform Integration + Flow Build (week 3-5)
- Deliverable: platform live; solicitation flows (email + SMS) configured; UGC rights-capture integrated
- Validation: test transactions produce review requests; rights capture in flow
- Target: end of week 5

### M3 — Response Protocol + Training (week 5-7)
- Deliverable: team trained; 48h response SLA on 1-3 star; crisis / escalation paths
- Validation: response metrics tracking; first week of responses executed
- Target: end of week 7

### M4 — Cross-Platform Posting (week 6-9)
- Deliverable: Google Seller Ratings + Trustpilot + ad platform integrations
- Validation: multi-platform review flow confirmed
- Target: end of week 9

### M5 — UGC Activation (week 8-11)
- Deliverable: UGC library curated; PDP UGC galleries live; paid-ad UGC creative library
- Validation: UGC driving measurable PDP lift in A/B test
- Target: end of week 11

### M6 — Performance Review + Iteration (week 11-12+)
- Deliverable: performance dashboard; monthly review cadence; iteration backlog
- Validation: program self-operating; KPIs trending
- Target: end of week 12+

## Step 3 — Critical mental model

Reviews and UGC are the third-most important conversion element on a PDP — after price and image — and they compound.

Each review adds to the social-proof library; each UGC photo adds to the visual trust library. Products with 50 reviews convert materially better than products with 5. Products with 200 reviews + 20 UGC photos dominate paid-ad CTR + on-site conversion.

This compounds: higher conversion → more sales → more reviews → higher conversion. Brands that invest in systematic solicitation at product launch capture the compound advantage. Brands that wait for organic reviews never catch up.

The flip side: one high-visibility 1-star review can crater a product's rating and conversion. Response protocol is insurance — when the rare catastrophe happens, professional response preserves trust.

## Step 4 — Domain validators

- Solicitation active: automated flow firing on 100% of eligible orders

- Response SLA: 1-3 star reviews with response within 48h

- UGC rights capture: every submission includes permission

- Cross-platform sync: Google / Trustpilot / ad platforms receiving data

- Review fraud monitoring: unusual patterns flagged for review

## Step 8 — Working protocol additions

- Never pay for reviews

- Never solicit positive-only

- Never filter negative reviews pre-publication

- Never argue publicly with negative reviewers

- Always respond to 1-3 stars within 48h

- Always capture rights with UGC submission

- Always cross-post to Google Seller Ratings for ad star-rating lift

## KB integration

- {{KNOWLEDGE_BASE_ROOT}}/retail-sales-enablement/wiki/_index.md — PDP + conversion patterns

- {{KNOWLEDGE_BASE_ROOT}}/product-research-and-competitive-intelligence/wiki/_index.md — competitive review analysis

## Common example fills

- "Launch Okendo review program for $20M DTC brand — target 10% review-to-purchase ratio, 4.3+ average rating"

- "Rebuild review-solicitation flow — current response rate 3%, target 15%"

- "UGC rights capture + ads library build — 200 rights-cleared UGC assets for paid media in 12 weeks"

- "Review crisis response — product-issue driving 1-star wave; response + product-fix coordination"

- "Cross-platform review footprint expansion — Google Seller Ratings + Trustpilot + BBB + Reviews.io"

## Hand-off

After bootstrap, use ~/.claude/templates/growth-ecommerce/ugc-reviews/resumption.md.