# Wholesale / Retail Expansion Program — Bootstrap

Inherits from: ~/.claude/templates/session-kickoff-bootstrap.md

Use when: entering wholesale / retail channels — specialty, mass, club, department store, chain, drug, convenience — from a DTC or Amazon-first starting point.

## Who this is for

Brand leaders, VPs of sales, directors of retail at DTC / CPG / consumer brands adding wholesale channels. Programs span 12-36 weeks depending on scope — retail selling cycles are long.

## Opinionated defaults

### Retail channel types

- Specialty (local stores, independents): highest margin, lowest volume, best for launch + brand building

- Mass (Target, Walmart): high volume, MAP-controlled, national reach

- Club (Costco, BJ's, Sam's): extreme volume, compressed margins, SKU specificity

- Department / chain (Nordstrom, Macy's, Dick's): curated assortment, elevated positioning

- Drug / convenience (CVS, Walgreens, 7-Eleven): impulse / replenishment, fast turnover expectation

- Omni-channel platforms (Amazon, Target+, Walmart Connect): marketplace-adjacent but act as channels

### Retail buyer process

- Pitch → pilot → scale → national: typically 6-24 months from first conversation to national rollout

- Category reviews: annual or biannual; miss the window = wait a year

- Retailer product-development calendar: plan 12-18 months out

- In-person matters at most retailers (Target, Whole Foods, REI, Dick's) — Zoom for pilot, in-person for scale

### Margin structure

- Keystone pricing: 50% margin wholesale-to-retail (standard)

- Actual spread: 35-55% depending on category + channel

- Trade spend: 10-20% of wholesale revenue typical (co-op, slotting, promos, demos)

- Chargebacks: 5-15% of wholesale revenue (returns, damages, short-ships, compliance fees)

- Net margin to brand: 15-30% of retail price after all deductions for most consumer categories

### MAP + channel conflict

- MAP policy required before entering multi-channel wholesale. Without it, Amazon discounters destroy retail partner relationships.

- Enforce MAP aggressively — the policy is only as strong as enforcement

- DTC pricing strategy: equal-to-MAP (preserves partners) or premium-to-MAP (partners offer discount, DTC captures direct margin)

- Channel-exclusive SKUs preserve retail relationships while allowing DTC flexibility

### Planogram + merchandising

- Primary driver of retail velocity: shelf location, facings, placement

- Store-level compliance audit required — sign-off on placement

- Planogram changes lag reality by months — don't assume your placement is current

- Shelf-back strategy: packaging designed for shelf context (dieline, colorway, hierarchy)

### Co-op + slotting

- Slotting fees: one-time payment for shelf space in some channels (500−50K per SKU per location). Category-dependent.

- Co-op marketing: ongoing promo support; typically 3-8% of wholesale revenue

- Demo programs: in-store sampling for velocity launch; high ROI if product is trial-driven

### Broker / rep model

- Broker: 5-8% commission; lower cost but less aligned with brand

- In-house sales rep: higher cost but owned relationship

- Hybrid: broker for small accounts, in-house for strategic accounts

- Manufacturer's rep organization (MRO): industry-specific; category-dependent fit

## Step 0 — Interview question additions

- Target channels — which retailers, in what sequence?

- Current retail presence — any existing wholesale relationships?

- DTC / Amazon revenue mix — how dependent on current channel economics?

- Product-category fit — is the product shelf-stable, display-ready, impulse-friendly?

- Inventory capacity — can you support retail orders without starving DTC?

- Pricing strategy — MAP policy exists? Enforceable?

- Packaging retail-ready? — dieline, barcoding, case pack, pallet spec

- Compliance infrastructure — EDI, GS1 barcodes, test-and-hold requirements, retail-specific labels

- Sales team / broker relationships — in-house, broker, MRO, none?

- Trade-spend budget — capacity for co-op + slotting + demos

- Freight / logistics — shipping to retail DCs (distribution centers) vs. store-direct

- Planning horizon — target retailers have calendars; which windows are you hitting?

## Step 2 — Milestone template (24-week program)

### M1 — Channel Strategy + Target List (week 1-3)
- Deliverable: prioritized retailer list; entry-sequence plan; pricing strategy
- Validation: MAP policy drafted; channel conflict mapped
- Target: end of week 3

### M2 — Retail Readiness (week 3-8)
- Deliverable: packaging retail-ready; compliance infrastructure (EDI, GS1); case-pack + pallet spec
- Validation: packaging passes retail requirements; compliance systems operational
- Target: end of week 8

### M3 — Buyer Pitch Wave (week 6-16)
- Deliverable: pitches delivered to target buyers; pitch deck, samples, category review
- Validation: pitches landed; follow-ups scheduled
- Target: end of week 16

### M4 — Pilot Program (week 12-20)
- Deliverable: pilot orders shipped; in-store placement confirmed
- Validation: product on shelf; sell-through tracking live
- Target: end of week 20

### M5 — Trade Spend + Co-op Activation (week 16-22)
- Deliverable: demo programs, co-op marketing, promo activation
- Validation: programs running; velocity improving
- Target: end of week 22

### M6 — Scale Decision + Expansion (week 22-24)
- Deliverable: sell-through review; expansion recommendations; reorder planning
- Validation: data-driven kill / scale / expand decision per retailer
- Target: end of week 24

## Step 3 — Critical mental model

Wholesale is not DTC with middlemen.

In DTC, you own the customer relationship and optimize for LTV. In wholesale, the retailer owns the customer relationship and optimizes for sell-through on their shelf. These are different businesses with different unit economics, timelines, and operational requirements.

The #1 mistake is thinking wholesale will be "like DTC but at scale." Wholesale requires: retail-ready packaging, EDI compliance, trade spend, planogram management, buyer relationships, retailer-calendar planning, MAP enforcement, chargeback management, and a sales motion with 6-24 month cycles.

Budget for this or don't enter wholesale. The brands that succeed have a dedicated retail team with retail-experienced leadership. The brands that fail try to bolt wholesale onto an ecommerce team with no retail DNA.

## Step 4 — Domain validators

- MAP policy enforceable: violations detectable + remediable within 14 days

- Packaging retail-ready: dieline, barcodes, case pack, pallet spec, claims compliant

- EDI operational: orders, invoices, ASNs flow cleanly

- Chargeback tracking: categorized by cause (returns, damages, compliance, short-ship, etc.)

- Sell-through data flowing: retailer POS data ingested weekly or monthly

## Step 8 — Working protocol additions

- Never enter wholesale without MAP policy + enforcement capacity

- Never under-estimate chargebacks — budget 5-15% of wholesale revenue

- Never miss a retailer calendar window — wait a year for next one

- Never over-commit inventory to DTC when retail order is imminent

- Never hide trade spend — full cost of wholesale includes it

- Always track sell-through, not just sell-in — sitting on shelf is bad

- Always over-communicate with buyers — retail relationships are personal

## KB integration

- {{KNOWLEDGE_BASE_ROOT}}/retail-sales-enablement/wiki/_index.md — 33 articles; primary reference for ShelfWins, planograms, buyer decks, retail strategy — read before M3

## Common example fills

- "Launch in Target — DTC skincare brand entering mass channel first time; 24-week program to category review + pilot"

- "Expand beverage brand from regional specialty (~200 doors) to national chain ($50M revenue target)"

- "Add Whole Foods + Sprouts for CPG brand currently DTC + Amazon — dual-tier natural-channel strategy"

- "Enter REI + Backcountry for outdoor-gear brand currently DTC-only — specialty-first retail strategy"

- "Recover underperforming wholesale program — 40% chargeback rate; diagnose + remediate"

## Hand-off

After bootstrap, use ~/.claude/templates/growth-ecommerce/wholesale-retail/resumption.md.